Agentic Research Plan

PRISM Theory Validation Program v1.0

A complete specification for dispatching the PRISM hydrogen-spectrum validation research to an agentic AI system. Designed to be PRISM Estimate v7.0.4-compatible: 17-agent role addressable, MCP-server-aware, with explicit input/output contracts, success criteria, escalation rules, and honest limits on what agents can and cannot do autonomously.

Principal:  Kip Madden

Version:    1.0

Generated:  April 16, 2026

Estimated wall time:  6–10 weeks

Estimated token budget:  800K–1.5M

# How to Use This Spec

This document is both a human-reviewable research plan and a machine-parseable specification. It is designed to be loaded into an agentic orchestrator that dispatches tasks across specialized sub-agents (theoretician, data-fetcher, computer, validator, critic, reporter) with explicit tool and MCP-server requirements.

Three audiences, three reading paths:

- Orchestrator agents: read Sections 1–6 for mission and agent role assignments, Section 8 for task graph, Sections 10 and 14 for escalation and termination rules.

- Sub-agents: read only your named task specifications in Section 8, plus the handoff contracts in Section 9.

- Kip (principal): Sections 1–3 set the frame, Section 11 lists your mandatory checkpoints, Section 13 is the honest list of what agents can't do for you.

The canonical machine-readable version lives in prism_research_plan_v1.0.md alongside this document. That file is the source of truth; this Word doc is the presentation layer.

# 1. Mission

Determine whether the PRISM framework — which proposes that atomic structure is a 4D Cartesian projection of a 5D logarithmic-spiral worldline with α as the native rotation-scaling coupling — produces quantitatively correct predictions for:

- The hydrogen Lamb shift (and the full Bethe-log function for n = 1..5)

- The proton radius discrepancy between electronic and muonic hydrogen

- The running of α with energy scale Q²

...from a single geometric parameter, without tuning any free parameter to the data being predicted.

# 2. Success Criteria

Must have

- PRISM-derived s-state correction produces Bethe-log values within 10% without fitting any parameter to hydrogen data

- Derivation is reproducible: another agent given the framework and the spec can re-derive the function independently

- Final report states clearly whether PRISM is VALIDATED, FALSIFIED, or INCONCLUSIVE at achievable precision

Should have

- Same derived function predicts muonic hydrogen Lamb shift within experimental uncertainty

- Cross-prediction for α(Q²) running agrees with LEP measurements

- Public-release-quality code artifacts in version-controlled repo

Nice to have

- Prediction for He⁺ (hydrogenic Z=2) spectrum

- Explanation of the 4% proton radius puzzle

- Paper draft suitable for arXiv submission

# 3. Constraints & Operating Assumptions

3.1 Hard constraints

Data sources allowed:

- NIST Atomic Spectra Database (static Handbook tables)

- NIST HDEL theoretical levels database

- CODATA 2022 fundamental constants

- Published peer-reviewed papers (CREMA for muonic H, LEP compilations for α running)

Data sources prohibited:

- Any source requiring credentials

- Non-peer-reviewed preprints as primary data (context only)

3.2 Challengeable assumptions

Any agent may flag these for review. They are operating assumptions, not settled facts:

- PRISM's 5D framework, as currently specified, is self-consistent enough to derive an explicit s-state correction function.

- The standard Bethe log is the correct target for comparison. PRISM might produce a different but equally valid QED decomposition.

- Reduced-mass and recoil effects factor cleanly from QED contributions. PRISM geometry may couple them non-trivially.

- 5-fold-symmetry / φ signatures are testable at currently-achievable precision. May require yet-unpublished precision.

# 4. Agent Roles

Nine distinct agent roles, named to be compatible with PRISM Estimate v7.0.4's 17-agent inventory. Multiple roles may be filled by the same underlying model; the distinction is responsibility and tool access, not necessarily deployment.

| Role | Responsibility | Tools / MCP |
| --- | --- | --- |
| orchestrator | Sequence phases, manage state, enforce checkpoints, route escalations. | state_manager, escalation_router |
| data_fetcher | Pull raw data from external sources with retry, cache, and validate. | web_fetch, web_search, filesystem |
| parser | Transform raw data (HTML, PDF, CSV) into structured typed records. | regex_engine, html_parser, filesystem |
| theoretician | Derive mathematical expressions from PRISM first principles. REQUIRES HUMAN-IN-THE-LOOP for every derivation step. | sympy, latex_renderer, filesystem |
| computer | Evaluate expressions numerically, run fits, generate predictions. | python (numpy, scipy, mpmath), pysr, code_execution |
| validator | Cross-check predictions against literature, compute confidence, flag anomalies. | statistical_tests, literature_lookup, web_search |
| critic | Red-team findings, propose alternative explanations, search for confounds. | literature_search, reasoning_chain |
| reporter | Synthesize all outputs into human-readable deliverables. | docx_generator, matplotlib, pandoc, latex |
| librarian | Maintain immutable knowledge base of literature values and prior art. | knowledge_store, citation_formatter |

# 5. Phase Overview

Seven phases. Phase 0 is already complete (v1–v4 pipelines + summary doc). Phase 1 is the critical path; everything downstream depends on its verdict. Phases 2–4 can run in parallel after Phase 1 passes.

| Phase | Name | Gate/Status | Runs in parallel with |
| --- | --- | --- | --- |
| 0 | Foundation | COMPLETE | — |
| 1 | First-principles derivation | CRITICAL PATH — go/no-go | nothing (all depend on this) |
| 2 | Muonic hydrogen cross-check | Unique PRISM claim | Phase 3, Phase 4 |
| 3 | α(Q²) running cross-check | Independent validation | Phase 2, Phase 4 |
| 4 | Symbolic regression confirmation | Sanity check | Phase 2, Phase 3 |
| 5 | Extended dataset | Robustness | sequential after 1 |
| 6 | Synthesis and publication | Deliverable | sequential after 2-5 |

# 6. Task Specifications

Each phase decomposes into 3-5 tasks. Each task is a complete contract: inputs, outputs, success criteria, estimated token budget. Tasks marked CRITICAL PATH block the entire program on failure. Tasks marked GATE require explicit verdict before downstream work continues. Tasks marked HUMAN-IN-THE-LOOP require Kip's review before the agent proceeds.

## Phase 1 — First-Principles Derivation

| P1-T1 Formalize PRISM framework for computation HUMAN-IN-THE-LOOP |  |
| --- | --- |
| Agent | theoretician |
| Inputs | • Kip's PRISM notes (provided) • PRISM framework v7.0.4 draft |
| Outputs | • prism_formal_spec.md • prism_coordinate_diagram.svg |
| Success criteria | • Every variable has a type, range, and physical interpretation • Every postulate stated without 'intuitively' or 'obviously' • Coordinate transformations (5D ↔ 4D) are explicit functions |
| Token budget | 20K–40K |

| P1-T2 Derive orbital wavefunction in 5D spiral basis HUMAN-IN-THE-LOOP |  |
| --- | --- |
| Agent | theoretician |
| Depends on | P1-T1 |
| Inputs | • prism_formal_spec.md |
| Outputs | • derivations/5d_wavefunction.tex • derivations/4d_projection.tex • derivations/angular_momentum_mapping.tex |
| Success criteria | • 5D wavefunction ψ(n, ℓ, j, χ, r) explicitly written (χ = 5th-dim coord) • 4D projection recovers standard hydrogen wavefunction in limit • Angular momentum quantization emerges from compactification topology, not postulated |
| Token budget | 60K–120K |

| P1-T3 Derive s-state-specific correction — THE CENTRAL CALCULATION CRITICAL PATH HUMAN-IN-THE-LOOP |  |
| --- | --- |
| Agent | theoretician |
| Depends on | P1-T2 |
| Inputs | • derivations/5d_wavefunction.tex |
| Outputs | • derivations/s_state_correction.tex • derivations/s_state_correction_formula.json |
| Success criteria | • Integral expression for s-state self-energy analog in native basis • Integral is finite and well-defined (no renormalization handwaves) • Expression is explicit function of n with no free parameters beyond α |
| Token budget | 80K–150K |

| P1-T4 Numerically evaluate derived expression for n = 1..5 |  |
| --- | --- |
| Agent | computer |
| Depends on | P1-T3 |
| Inputs | • derivations/s_state_correction_formula.json |
| Outputs | • predictions/prism_bethe_log_analog.csv • predictions/numerical_method_log.md |
| Success criteria | • Values computed to 6 sig figs with documented error estimate • Numerical method (quadrature, convergence test) documented • Cross-check with independent method agrees to 4+ sig figs |
| Token budget | 10K–20K |

| P1-T5 Compare PRISM prediction to measured Bethe log GATE |  |
| --- | --- |
| Agent | validator |
| Depends on | P1-T4 |
| Inputs | • predictions/prism_bethe_log_analog.csv • Drake & Swainson 1990 values |
| Outputs | • validation/phase1_verdict.md • figures/phase1_comparison.png |
| Success criteria | • Comparison table: predicted vs measured, n = 1..5 • Relative error computed for each • Verdict: VALIDATED (<10%) / PARTIAL (<50%) / FALSIFIED (>50% or wrong sign) |
| Token budget | 5K–10K |

## Phase 2 — Muonic Hydrogen Cross-Check

| P2-T1 Fetch CREMA muonic hydrogen measurements |  |
| --- | --- |
| Agent | data_fetcher |
| Depends on | P1-T5 = VALIDATED or PARTIAL |
| Inputs | • Pohl et al. Nature 2010 • Antognini et al. Science 2013 |
| Outputs | • raw_data/muonic_h_lamb_shift.csv • raw_data/muonic_h_citations.bib |
| Success criteria | • Primary μH(2S-2P) measurements obtained • Uncertainties documented • Citations preserved |
| Token budget | 30K–50K |

| P2-T2 Apply PRISM function to muonic system |  |
| --- | --- |
| Agent | computer |
| Depends on | P1-T3, P2-T1 |
| Inputs | • derived formula • muon mass, muonic Bohr radius |
| Outputs | • predictions/muonic_h_lamb_shift.csv • predictions/proton_radius_prediction.json |
| Success criteria | • Predicted muonic Lamb shift computed • Predicted proton radius from muonic probe computed • If PRISM couples to reduced mass via compactification, coupling recorded |
| Token budget | 10K–20K |

| P2-T3 Validate against measured muonic Lamb shift + proton radius puzzle GATE |  |
| --- | --- |
| Agent | validator |
| Depends on | P2-T2 |
| Inputs | • predictions • measurements • proton_radius_puzzle knowledge base |
| Outputs | • validation/phase2_verdict.md • figures/muonic_vs_electronic_proton_radius.png |
| Success criteria | • σ-difference between predicted and measured muonic Lamb shift • Explicit test: does PRISM predict the 4% electronic/muonic proton radius gap? • Verdict: VALIDATED / PARTIAL / FALSIFIED |
| Token budget | 10K |

## Phase 3 — α(Q²) Running Cross-Check

| P3-T1 Fetch α running data from LEP / PDG compilations |  |
| --- | --- |
| Agent | data_fetcher |
| Depends on | P1-T5 |
| Inputs | • Jegerlehner 2019 compilation • PDG electroweak fits |
| Outputs | • raw_data/alpha_running.csv • raw_data/alpha_running_citations.bib |
| Success criteria | • α values at multiple Q² scales, low energy to M_Z • Systematic uncertainties documented |
| Token budget | 30K |

| P3-T2 Derive α running from PRISM geometry HUMAN-IN-THE-LOOP |  |
| --- | --- |
| Agent | theoretician |
| Depends on | P1-T1 |
| Inputs | • prism_formal_spec.md |
| Outputs | • derivations/alpha_running_from_geometry.tex • predictions/alpha_q2_prism.csv |
| Success criteria | • Derivation uses same compactification parameter as Phase 1 (no new free parameters) • Functional form α(Q²) from pure geometry |
| Token budget | 60K–100K |

| P3-T3 Validate α running prediction GATE |  |
| --- | --- |
| Agent | validator |
| Depends on | P3-T1, P3-T2 |
| Inputs | • predictions • LEP measurements |
| Outputs | • validation/phase3_verdict.md • figures/alpha_running_prism_vs_data.png |
| Success criteria | • σ-difference at each measured Q² • Verdict |
| Token budget | 10K |

## Phase 4 — Symbolic Regression Sanity Check

Data-driven discovery of the functional form, as independent cross-check of the analytic derivation.

| P4-T1 Run PySR with PRISM-constrained operator basis |  |
| --- | --- |
| Agent | computer |
| Depends on | P1-T5 |
| Inputs | • v4 pipeline residuals (from prism_hydrogen_v4.py output) • Operator basis: {+, -, *, /, log, sin, cos, exp} • Constants: {1, α, π, φ, n, ℓ, j} |
| Outputs | • pysr_fits/top_10_expressions.csv • pysr_fits/pareto_frontier.png |
| Success criteria | • 40+ iterations • Top expression R² > 0.99 |
| Token budget | 15K + 4-8h compute |

| P4-T2 Algebraic comparison: discovered form vs derived form |  |
| --- | --- |
| Agent | validator |
| Depends on | P4-T1, P1-T3 |
| Inputs | • PySR top expression • derived expression |
| Outputs | • validation/phase4_verdict.md |
| Success criteria | • Algebraic simplification of both to canonical form • If equivalent: HIGH CONFIDENCE flag • If different: flag for critic review |
| Token budget | 10K |

## Phase 5 — Extended Dataset (Robustness)

Apply the derived function, unchanged, across multiple hydrogenic systems. If it predicts all of them correctly without system-specific tuning, the framework's generality is established.

- P5-T1 — fetch deuterium spectrum from NIST Handbook

- P5-T2 — fetch NIST HDEL high-n (to n=200) via proxy workaround

- P5-T3 — fetch He⁺ (Z=2 hydrogenic) spectrum

- P5-T4 — apply derived function across all systems, Z and mass only variables

- P5-T5 — validate extended predictions (GATE task)

## Phase 6 — Synthesis and Publication

| P6-T1 Critic red-team pass |  |
| --- | --- |
| Agent | critic |
| Depends on | all validation phases |
| Inputs | • all validation reports • all derivations |
| Outputs | • red_team_report.md • recommended_null_tests.md |
| Success criteria | • ≥3 alternative explanations considered • ≥2 specific falsification experiments suggested |
| Token budget | 40K |

| P6-T2 Draft paper HUMAN-IN-THE-LOOP |  |
| --- | --- |
| Agent | reporter |
| Depends on | P6-T1 |
| Inputs | • all artifacts |
| Outputs | • paper_draft.tex • paper_draft.pdf • figures/publication_quality/*.pdf |
| Success criteria | • 4000–6000 words • Complete sections: abstract, intro, framework, derivation, results, discussion, conclusion • Figures at 300 DPI, arXiv-compatible bibliography |
| Token budget | 80K–150K |

| P6-T3 Reproducibility package |  |
| --- | --- |
| Agent | reporter |
| Depends on | P6-T2 |
| Inputs | • all artifacts |
| Outputs | • github_ready/code/ • github_ready/data/ (with provenance) • github_ready/derivations/ • github_ready/README.md, LICENSE, CITATION.cff |
| Success criteria | • Fresh clone + single command reproduces all results |
| Token budget | 15K |

# 7. Handoff Contracts

Every file produced by any task includes a YAML frontmatter block with metadata, so downstream tasks don't re-parse prose:

--- generated_by: <agent_id> generated_at: <ISO-8601 timestamp> depends_on: [<list of input file hashes>] spec_task_id: <P#-T#> ---

File format conventions:

- data files: CSV with header row; schema in adjacent .yaml

- derivations: .tex for human reading; .json with extracted formulas for machines

- predictions: CSV columns [system, n, l, j, quantity, predicted, uncertainty, method]

- validation: Markdown with required sections [summary, table, verdict, recommendations]

- figures: PNG for review, PDF for publication

# 8. Escalation Rules

Automatic escalation to Kip

- Any derivation step makes a non-first-principles choice

- Predicted vs measured differs by >5σ with no known cause

- Framework inconsistency detected

- Data source returns unexpected format 3 times in a row

- Token budget for phase exceeded 2×

Pause and report (logged, not escalated)

- Retry with backoff succeeds after 1–2 attempts

- Literature value has a known superseding revision

- Alternative derivation path available

Auto-proceed

- Routine data fetch and parse

- Numerical evaluation of validated formulas

- Fit convergence within tolerance

# 9. Human Checkpoints (Mandatory)

- After P1-T1 — Kip approves formalized framework before derivation

- After P1-T3 — Kip reviews each step of s-state derivation

- After P1-T5 — Go/no-go decision for phases 2–5 based on verdict

- After all validation phases — decision to proceed to publication

- After P6-T2 — final review before any external release

# 10. Kill Criteria

The program is formally terminated (not paused) if any of these trigger:

- P1-T5 returns FALSIFIED and Kip determines the framework cannot be rescued without becoming unfalsifiable

- More than 2 separate assumptions (Section 3) require escalation to 'new postulate' status, making the framework untestable

- Required data is demonstrated to not exist at needed precision and cannot be obtained

- Six months elapse with no Phase 1 completion

Termination is a legitimate outcome. A well-documented negative result (PRISM cannot produce the Bethe log from first principles at current specification) is publishable and advances the framework's development by constraining its requirements.

# 11. Honest Limits of Agentic Execution

This is the section worth reading twice. The spec is designed so agents do what agents actually do well and humans do what only humans can do. Both sets matter.

## 11.1 What agents cannot fully automate in this program

- Theoretical derivations (P1-T2, P1-T3, P3-T2): this is original theoretical physics. AI can propose steps, verify algebra, and critique derivations, but cannot substitute for human mathematical creativity at current SOTA. Human-in-the-loop is non-negotiable.

- Framework consistency judgment: if a derivation appears to need a new postulate, only Kip can decide whether that's an acceptable extension or a retreat from falsifiability.

- Peer-review substitute: the critic agent red-teams but does not replicate domain expert review. External physicist review is recommended before any public release.

## 11.2 What agents can fully automate

- All data fetching, parsing, validation

- Numerical evaluation of established formulas

- Statistical fitting and model comparison

- Figure generation and report writing

- Literature lookup and citation formatting

- Symbolic regression (human review of outputs)

## 11.3 Design implication

The critical path (Phase 1) is dominated by tasks requiring human-in-the-loop. This is not a limitation of the spec — it is the spec being honest about where AI assistance ends and original research begins. The value of running this program agentically is not in replacing Kip's theoretical work; it is in keeping the bookkeeping, data plumbing, numerical evaluation, and synthesis overhead from consuming his time so he can focus on the derivations themselves.

Put another way: the agents are the scaffolding; the physics is yours. The spec's job is to make sure the scaffolding holds up so you can climb.

# Appendix A: Literature Priors

The librarian agent pre-populates the knowledge base with these values. They are targets for prediction and comparison, not inputs to any derivation.

bethe_log_values: n_1: 2.984128556 # Drake & Swainson 1990 n_2: 2.811769893 n_3: 2.767663612 n_4: 2.749811840 n_5: 2.740823727 hydrogen_lamb_shift_MHz: 1057.845 +/- 0.009 source: Lundeen & Pipkin, PRL 46, 232 (1981) muonic_hydrogen_lamb_shift_meV: 0.2065 source: Antognini et al., Science 339, 417 (2013) proton_radius_electronic_fm: 0.8775 +/- 0.0051 # CODATA 2018 proton_radius_muonic_fm: 0.84087 +/- 0.00039 # CREMA 2013 alpha_at_m_e: 0.0072973525643 # CODATA 2022 alpha_at_M_Z: 0.007816 +/- 0.000005 # Jegerlehner 2019

# Appendix B: Starting State

Phase 0 is already complete. The following artifacts exist and are the starting state for the program:

- prism_hydrogen_v1.py — baseline pipeline, hand-curated data

- prism_hydrogen_v2.py — fine-structure + BIC model selection

- prism_hydrogen_v3.py — live NIST fetch, Lamb shift to 99.96% of literature

- prism_hydrogen_v4.py — reduced-mass corrected, clean QED extraction

- prism_research_summary.docx — human-readable summary with findings

v4 current findings (input to Phase 1 context):

- Qualitative PRISM prediction: CONFIRMED — s-states feel extra coupling, pattern scales correctly

- Quantitative ansatz: FAILED — fit coefficient wrong sign and ~4.5× off from Bethe log

- φ-modulation: MARGINAL (2.7σ) — neither confirmed nor ruled out

- Net interpretation: geometric intuition correct; functional form guess wrong. Phase 1 addresses exactly this.

# Appendix C: Spec Self-Test

The orchestrator runs this self-test before dispatching Phase 1:

- Can the mission be evaluated objectively? — YES (binary success criteria)

- Can each task run with only its declared inputs? — verified per task at dispatch

- Is every agent role bounded? — YES (explicit responsibilities)

- Is every tool dependency explicit? — YES (Section 4 + per task)

- Are escalation paths defined for every failure mode? — YES (Section 8)

- Is there a kill criterion? — YES (Section 10)

- Is human-in-the-loop explicit where needed? — YES (tagged per task)

- Are deliverables concrete? — YES (Section 6 task outputs + final deliverables)